NBA PLAYER PROP PROJECTIONS

JIRA SPECIFICATION & SPRINT PLAN

Moneyball Sports Betting System  |  Player Layer & ML Extension  |  Version 1.0  |  February 2026

| Project | Moneyball Sports Betting | Scope | 3–6 months part-time |
| --- | --- | --- | --- |
| Module | Player Layer & ML Extension | Total Story Points | 199 |
| Version | 1.0 | Total Sprints | 10 (20 weeks) |

# Executive Summary

This specification extends the existing NBA sports betting system with comprehensive player-level data ingestion and machine learning capabilities for player prop projections. The system will ingest player profiles, season statistics, and game-by-game performance data from the SportRadar API, store them relationally in SQL Server, and train multiple ML models per stat category to predict player performance.

Key Deliverables:

- Player data layer (Players, PlayerSeasonStats, PlayerGameStats tables)

- Player data ingestion pipeline from SportRadar API

- ML feature engineering framework with rolling averages, splits, and opponent context

- Multi-model training and comparison system (Linear Regression, Random Forest, XGBoost, LightGBM)

- Prediction API endpoints (single player and batch)

- Comprehensive unit and integration test coverage (90%+)

# Sprint Planning Overview

The project is organized into 10 two-week sprints across approximately 20 weeks. Sprints are sequenced to respect epic dependencies: the data layer must exist before ingestion, features before ML training, and models before the prediction API.

| Sprint | Dates | Points | Focus / Goal |
| --- | --- | --- | --- |
| Sprint 1 | Weeks 1–2 | 21 | Player Data Layer Foundation Core database schema and entity framework in place. Team can insert and query player records. |
| Sprint 2 | Weeks 3–4 | 19 | Feature Views & Calculators Feature engineering view operational and API client ready for ingestion work. |
| Sprint 3 | Weeks 5–6 | 26 | Ingestion Pipeline Full ingestion pipeline operational. Data flows from SportRadar into SQL Server nightly. |
| Sprint 4 | Weeks 7–8 | 21 | Feature Engineering All ML features computed and validated. Ready for model training. |
| Sprint 5 | Weeks 9–10 | 26 | ML Models – Part 1 Linear and Random Forest models trained and persisted. Baseline metrics established. |
| Sprint 6 | Weeks 11–12 | 29 | ML Models – Part 2 All four model types trained and compared. Best model selected per stat category. |
| Sprint 7 | Weeks 13–14 | 26 | Prediction API Prediction endpoints live. Single and batch predictions returning results. |
| Sprint 8 | Weeks 15–16 | 21 | Testing & QA 90%+ unit test coverage achieved. All entity and calculator tests passing. |
| Sprint 9 | Weeks 17–18 | 21 | Integration Tests & Docs All integration tests passing. Documentation complete. System ready for production. |
| Sprint 10 | Weeks 19–20 | 11 | Deployment & Monitoring Production deployment complete. Monitoring live. Sprint buffer for bug fixes. |

## Sprint Story Assignments

Sprint 1: Player Data Layer Foundation

| Story / Task | Points |
| --- | --- |
| MBALL-301 (8pts): DB Schema |  |
| MBALL-302 (5pts): Entities & DTOs |  |
| MBALL-303 (5pts): Repositories |  |
| MBALL-305 (3pts): Derived Stats |  |

Sprint 2: Feature Views & Calculators

| Story / Task | Points |
| --- | --- |
| MBALL-304 (8pts): ML_PlayerFeatures View |  |
| MBALL-306 (3pts): DraftKings Calculator |  |
| MBALL-311 (8pts): SportRadar API Integration |  |

Sprint 3: Ingestion Pipeline

| Story / Task | Points |
| --- | --- |
| MBALL-312 (13pts): Player Ingestion Service |  |
| MBALL-313 (8pts): Season Stats Aggregation |  |
| MBALL-314 (2pts): Minutes Parser |  |
| MBALL-315 (3pts): DNP Handling |  |

Sprint 4: Feature Engineering

| Story / Task | Points |
| --- | --- |
| MBALL-321 (5pts): Rolling Averages |  |
| MBALL-322 (3pts): Home/Away Splits |  |
| MBALL-323 (3pts): Rest Days & B2B |  |
| MBALL-324 (5pts): Opponent Defense |  |
| MBALL-325 (2pts): Pace Proxy |  |
| MBALL-326 (3pts): Usage Proxy |  |

Sprint 5: ML Models – Part 1

| Story / Task | Points |
| --- | --- |
| MBALL-331 (8pts): Python Training Pipeline |  |
| MBALL-332 (5pts): Linear Regression |  |
| MBALL-333 (8pts): Random Forest |  |
| MBALL-337 (5pts): Model Persistence |  |

Sprint 6: ML Models – Part 2

| Story / Task | Points |
| --- | --- |
| MBALL-334 (8pts): XGBoost |  |
| MBALL-335 (8pts): LightGBM |  |
| MBALL-336 (5pts): Model Comparison |  |
| MBALL-338 (5pts): Cross-Validation |  |
| MBALL-339 (8pts): Hyperparameter Tuning |  |

Sprint 7: Prediction API

| Story / Task | Points |
| --- | --- |
| MBALL-341 (8pts): Python Inference Service |  |
| MBALL-342 (8pts): C# Prediction Controller |  |
| MBALL-343 (5pts): Batch Predictions |  |
| MBALL-346 (3pts): Fallback Strategy |  |
| MBALL-344 (5pts): Caching Layer |  |

Sprint 8: Testing & QA

| Story / Task | Points |
| --- | --- |
| MBALL-351 (5pts): Entity Unit Tests |  |
| MBALL-352 (8pts): Ingestion Unit Tests |  |
| MBALL-353 (5pts): Calculator Tests |  |
| MBALL-345 (5pts): Confidence Scoring |  |

Sprint 9: Integration Tests & Docs

| Story / Task | Points |
| --- | --- |
| MBALL-354 (8pts): ML Pipeline Integration Tests |  |
| MBALL-355 (5pts): API Integration Tests |  |
| MBALL-361 (5pts): Technical Documentation |  |
| MBALL-362 (3pts): Migration Scripts |  |

Sprint 10: Deployment & Monitoring

| Story / Task | Points |
| --- | --- |
| MBALL-363 (3pts): Python Env Setup |  |
| MBALL-364 (5pts): Monitoring Dashboard |  |
| MBALL-345 (3pts): Final validation & Buffer |  |

# Epics, Stories, Tasks & Subtasks

Each epic below contains its constituent stories with full acceptance criteria and task breakdowns. Tasks include role assignments and sprint allocation.

| MBALL-300 EPIC 1: PLAYER DATA LAYER FOUNDATION |  |  |  |  |
| --- | --- | --- | --- | --- |
| Story Points | 21 | Priority | Critical |  |
| Dependencies | Existing Teams, Games tables |  |  |  |

| MBALL-301 Design and Implement Player Database Schema |  |  |  |
| --- | --- | --- | --- |
| Story Points | 8 | Priority | Critical |
| Acceptance Criteria |  |  |  |
| - Players table created with all profile fields |  |  |  |
| - PlayerSeasonStats table with unique constraints |  |  |  |
| - PlayerGameStats table with game-level stats |  |  |  |
| - MLPlayerModels table for model metadata |  |  |  |
| - All foreign key relationships defined |  |  |  |
| - Indexes optimized for prop queries |  |  |  |
| - Computed columns for PRA, double-doubles, fantasy scores |  |  |  |
| Task | Role | Est. | Sprint |
| Create Players table with profile fields | Dev | 2h | In Sprint 1 |
| Add unique constraint on ExternalPlayerId | Dev | 0.5h | In Sprint 1 |
| Create PlayerSeasonStats table with season aggregations | Dev | 1h | In Sprint 1 |
| Add unique constraint on (PlayerId, Season, TeamId) | Dev | 0.5h | In Sprint 1 |
| Create PlayerGameStats table with game-by-game stats | Dev | 1h | In Sprint 1 |
| Add unique constraint on (PlayerId, GameId) | Dev | 0.5h | In Sprint 1 |
| Add computed columns for IsDoubleDouble, IsTripleDouble | Dev | 1h | In Sprint 1 |
| Add computed column for DraftKingsFantasyScore | Dev | 1h | In Sprint 1 |
| Create indexes on PlayerId + GameId DESC | Dev | 1h | In Sprint 1 |
| Create index on GameId for boxscore queries | Dev | 0.5h | In Sprint 1 |
| Create filtered index excluding DNPs | Dev | 0.5h | In Sprint 1 |
| Create MLPlayerModels table for model tracking | Dev | 1h | In Sprint 1 |
| Add index on (StatCategory, IsBestModel) | Dev | 0.5h | In Sprint 1 |
| Write migration script with rollback | Dev | 2h | In Sprint 1 |
| Document schema in technical wiki | Dev | 1h | In Sprint 1 |

| MBALL-302 Create Player Entity Classes and DTOs |  |  |  |
| --- | --- | --- | --- |
| Story Points | 5 | Priority | Critical |
| Acceptance Criteria |  |  |  |
| - Player, PlayerSeasonStat, PlayerGameStat entities match schema |  |  |  |
| - PlayerProfileDto maps to SportRadar player API format |  |  |  |
| - SeasonStatsDto handles averages and totals |  |  |  |
| - GameBoxscoreDto with nested player arrays |  |  |  |
| - PlayerGameStatsDto with all stat fields |  |  |  |
| - Navigation properties configured |  |  |  |
| Task | Role | Est. | Sprint |
| Create Player entity class with all fields | Dev | 1h | In Sprint 1 |
| Create PlayerSeasonStat entity with navigation properties | Dev | 1h | In Sprint 1 |
| Create PlayerGameStat entity with computed properties | Dev | 1h | In Sprint 1 |
| Create MLPlayerModel entity | Dev | 0.5h | In Sprint 1 |
| Create PlayerProfileDto for API ingestion | Dev | 1h | In Sprint 1 |
| Create SeasonStatsDto with nested objects | Dev | 1h | In Sprint 1 |
| Create GameBoxscoreDto structure | Dev | 1h | In Sprint 1 |
| Create PlayerGameStatsDto with statistics object | Dev | 1h | In Sprint 1 |
| Add XML documentation to all classes | Dev | 1h | In Sprint 1 |
| Configure EF Core entity mappings | Dev | 1h | In Sprint 1 |
| Add Data Annotations for validation | Dev | 0.5h | In Sprint 1 |
| Write unit tests for DTO mapping | Dev | 1h | In Sprint 1 |

| MBALL-303 Implement Player Repository Interfaces |  |  |  |
| --- | --- | --- | --- |
| Story Points | 5 | Priority | High |
| Acceptance Criteria |  |  |  |
| - IPlayerRepository with CRUD and query methods |  |  |  |
| - IPlayerGameStatsRepository with rolling average queries |  |  |  |
| - IMLPlayerModelRepository for model management |  |  |  |
| - Async methods throughout |  |  |  |
| - Unit of Work pattern integration |  |  |  |
| Task | Role | Est. | Sprint |
| Define IPlayerRepository interface | Dev | 0.5h | In Sprint 1 |
| Add GetByExternalIdAsync method | Dev | 0.5h | In Sprint 1 |
| Add GetActivePlayersAsync method | Dev | 0.5h | In Sprint 1 |
| Add GetPlayersByTeamAsync method | Dev | 0.5h | In Sprint 1 |
| Add GetWithStatsAsync for eager loading | Dev | 0.5h | In Sprint 1 |
| Define IPlayerGameStatsRepository interface | Dev | 0.5h | In Sprint 1 |
| Add GetPlayerGameStatsAsync(playerId, lastN) | Dev | 0.5h | In Sprint 1 |
| Add GetGameBoxscoreAsync method | Dev | 0.5h | In Sprint 1 |
| Add GetRecentStatsForMLAsync method | Dev | 1h | In Sprint 1 |
| Define IMLPlayerModelRepository interface | Dev | 0.5h | In Sprint 1 |
| Add GetBestModelForStatAsync method | Dev | 0.5h | In Sprint 1 |
| Add SetBestModelAsync method | Dev | 0.5h | In Sprint 1 |
| Implement concrete repository classes | Dev | 2h | In Sprint 1 |
| Register repositories in DI container | Dev | 0.5h | In Sprint 1 |
| Write repository integration tests | Dev | 1h | In Sprint 1 |

| MBALL-304 Build ML_PlayerFeatures View |  |  |  |
| --- | --- | --- | --- |
| Story Points | 8 | Priority | High |
| Acceptance Criteria |  |  |  |
| - View generates rolling averages (L3, L5, L10) |  |  |  |
| - Season averages included |  |  |  |
| - Home/away splits calculated |  |  |  |
| - Rest days and back-to-back flag computed |  |  |  |
| - Opponent context available |  |  |  |
| - Excludes DNPs from features |  |  |  |
| - Performant for training queries |  |  |  |
| Task | Role | Est. | Sprint |
| Design CTE structure for window functions | Dev | 1h | In Sprint 2 |
| Implement GameContext CTE | Dev | 0.5h | In Sprint 2 |
| Implement RecentGames CTE with ROWS BETWEEN windowing | Dev | 1h | In Sprint 2 |
| Calculate L3 averages for all target stats | Dev | 1h | In Sprint 2 |
| Calculate L5 averages for all target stats | Dev | 0.5h | In Sprint 2 |
| Calculate L10 averages for all target stats | Dev | 0.5h | In Sprint 2 |
| Implement HomeSplits CTE | Dev | 1h | In Sprint 2 |
| Calculate home vs away performance | Dev | 0.5h | In Sprint 2 |
| Implement RestDays CTE with LAG function | Dev | 1h | In Sprint 2 |
| Add IsBackToBack calculation | Dev | 0.5h | In Sprint 2 |
| Join to PlayerSeasonStats for season averages | Dev | 0.5h | In Sprint 2 |
| Add opponent team context | Dev | 1h | In Sprint 2 |
| Add pace proxy (total score) | Dev | 0.5h | In Sprint 2 |
| Create indexes to support view queries | Dev | 0.5h | In Sprint 2 |
| Test query performance on 10K+ rows | Dev | 1h | In Sprint 2 |
| Document feature engineering logic | Dev | 0.5h | In Sprint 2 |

| MBALL-305 Create Derived Stat Calculator Utility |  |  |  |
| --- | --- | --- | --- |
| Story Points | 3 | Priority | Medium |
| Acceptance Criteria |  |  |  |
| - IsDoubleDouble method checks 2+ categories at 10+ |  |  |  |
| - IsTripleDouble method checks 3+ categories at 10+ |  |  |  |
| - CalculateRollingAverage handles variable N |  |  |  |
| - Excludes DNPs automatically |  |  |  |
| - Handles edge cases (insufficient data) |  |  |  |
| Task | Role | Est. | Sprint |
| Create DerivedStatCalculator class | Dev | 0.5h | In Sprint 1 |
| Implement IsDoubleDouble method | Dev | 0.5h | In Sprint 1 |
| Check Points, Rebounds, Assists, Steals, Blocks >= 10 | Dev | 0.5h | In Sprint 1 |
| Implement IsTripleDouble method | Dev | 0.5h | In Sprint 1 |
| Implement CalculateRollingAverage method | Dev | 1h | In Sprint 1 |
| Add LINQ ordering by GameId DESC | Dev | 0.5h | In Sprint 1 |
| Add Take(N) for last N games | Dev | 0.5h | In Sprint 1 |
| Filter out DidNotPlay = true | Dev | 0.5h | In Sprint 1 |
| Handle empty result sets | Dev | 0.5h | In Sprint 1 |
| Write comprehensive unit tests with Theory tests | Dev | 1h | In Sprint 1 |
| Test edge cases (0 games, 1 game, etc.) | Dev | 0.5h | In Sprint 1 |
| Document calculation logic | Dev | 0.5h | In Sprint 1 |

| MBALL-306 Build DraftKings Fantasy Calculator |  |  |  |
| --- | --- | --- | --- |
| Story Points | 3 | Priority | Medium |
| Acceptance Criteria |  |  |  |
| - Correct point values: Pts(1), 3PM(0.5), Reb(1.25), Ast(1.5), Stl(2), Blk(2), TO(-0.5) |  |  |  |
| - Double-double bonus: +1.5 |  |  |  |
| - Triple-double bonus: +3.0 (not +1.5) |  |  |  |
| - ProjectFantasyScore uses probability-weighted bonuses |  |  |  |
| - All calculations match DraftKings official scoring |  |  |  |
| Task | Role | Est. | Sprint |
| Create DraftKingsFantasyCalculator class | Dev | 0.5h | In Sprint 2 |
| Define point value constants | Dev | 0.5h | In Sprint 2 |
| Implement CalculateFantasyScore method | Dev | 1h | In Sprint 2 |
| Calculate base score from stats | Dev | 0.5h | In Sprint 2 |
| Add triple-double check and +3.0 bonus | Dev | 0.5h | In Sprint 2 |
| Add double-double check and +1.5 bonus (if not TD) | Dev | 0.5h | In Sprint 2 |
| Implement ProjectFantasyScore method | Dev | 1h | In Sprint 2 |
| Calculate expected value of bonuses | Dev | 0.5h | In Sprint 2 |
| Write unit tests for all scoring scenarios | Dev | 1h | In Sprint 2 |
| Test with real DraftKings examples | Dev | 0.5h | In Sprint 2 |
| Verify no double-counting of bonuses | Dev | 0.5h | In Sprint 2 |
| Document DraftKings scoring rules | Dev | 0.5h | In Sprint 2 |

| MBALL-310 EPIC 2: PLAYER DATA INGESTION PIPELINE |  |  |  |  |
| --- | --- | --- | --- | --- |
| Story Points | 34 | Priority | Critical |  |
| Dependencies | MBALL-300 (Player Data Layer) |  |  |  |

| MBALL-311 Implement SportRadar Player API Integration |  |  |  |
| --- | --- | --- | --- |
| Story Points | 8 | Priority | Critical |
| Acceptance Criteria |  |  |  |
| - GetNBAPlayersAsync fetches all active players |  |  |  |
| - GetPlayerProfileAsync retrieves individual profile |  |  |  |
| - GetPlayerSeasonStatsAsync fetches season aggregates |  |  |  |
| - GetGameBoxscoreAsync retrieves full boxscore with all players |  |  |  |
| - Rate limiting implemented (1 request per second) |  |  |  |
| - Circuit breaker for API failures |  |  |  |
| Task | Role | Est. | Sprint |
| Add SportRadar player endpoints to SportsDataService | Dev | 1h | In Sprint 2 |
| Implement GetNBAPlayersAsync method | Dev | 1h | In Sprint 2 |
| Parse player list response | Dev | 1h | In Sprint 2 |
| Implement GetPlayerProfileAsync(playerId) | Dev | 1h | In Sprint 2 |
| Implement GetPlayerSeasonStatsAsync(playerId, season) | Dev | 1h | In Sprint 2 |
| Parse season stats with averages and totals | Dev | 1h | In Sprint 2 |
| Implement GetGameBoxscoreAsync(gameId) | Dev | 1h | In Sprint 2 |
| Parse home and away player arrays | Dev | 1h | In Sprint 2 |
| Add rate limiting (1 req/sec) | Dev | 1h | In Sprint 2 |
| Add circuit breaker pattern | Dev | 1h | In Sprint 2 |
| Add retry logic with exponential backoff | Dev | 1h | In Sprint 2 |
| Write integration tests with mock responses | Dev | 2h | In Sprint 2 |
| Document API endpoints and responses | Dev | 0.5h | In Sprint 2 |
| Add logging for all API calls | Dev | 0.5h | In Sprint 2 |

| MBALL-312 Build Player Ingestion Service |  |  |  |
| --- | --- | --- | --- |
| Story Points | 13 | Priority | Critical |
| Acceptance Criteria |  |  |  |
| - IngestNBAPlayersAsync upserts all players |  |  |  |
| - Idempotent - can run multiple times |  |  |  |
| - Updates existing players on profile changes |  |  |  |
| - IngestPlayerGameStatsAsync processes date range |  |  |  |
| - Creates or updates PlayerGameStat records |  |  |  |
| - Handles DNP cases correctly |  |  |  |
| - Transaction per game for data consistency |  |  |  |
| Task | Role | Est. | Sprint |
| Create PlayerIngestionService class | Dev | 0.5h | In Sprint 3 |
| Implement IngestNBAPlayersAsync method | Dev | 1h | In Sprint 3 |
| Fetch all players from SportRadar | Dev | 0.5h | In Sprint 3 |
| Check if player exists by ExternalPlayerId | Dev | 0.5h | In Sprint 3 |
| Create new player if not exists | Dev | 0.5h | In Sprint 3 |
| Update existing player profile | Dev | 0.5h | In Sprint 3 |
| Implement MapToPlayer helper method | Dev | 1h | In Sprint 3 |
| Implement UpdatePlayerFromProfile helper | Dev | 0.5h | In Sprint 3 |
| Add transaction and save changes | Dev | 0.5h | In Sprint 3 |
| Implement IngestPlayerGameStatsAsync method | Dev | 1h | In Sprint 3 |
| Fetch completed games in date range | Dev | 0.5h | In Sprint 3 |
| Fetch boxscore for each game | Dev | 0.5h | In Sprint 3 |
| Process home team players | Dev | 0.5h | In Sprint 3 |
| Process away team players | Dev | 0.5h | In Sprint 3 |
| Implement UpsertPlayerGameStatAsync | Dev | 1h | In Sprint 3 |
| Check if stat exists (PlayerId, GameId) | Dev | 0.5h | In Sprint 3 |
| Create or update PlayerGameStat | Dev | 0.5h | In Sprint 3 |
| Implement MapToPlayerGameStat helper | Dev | 1h | In Sprint 3 |
| Parse minutes string MM:SS | Dev | 0.5h | In Sprint 3 |
| Handle DidNotPlay flag and reason | Dev | 0.5h | In Sprint 3 |
| Add comprehensive logging | Dev | 0.5h | In Sprint 3 |
| Write unit tests with FluentAssertions | Dev | 2h | In Sprint 3 |
| Test idempotency (run twice, same result) | Dev | 1h | In Sprint 3 |

| MBALL-313 Create Season Stats Aggregation Job |  |  |  |
| --- | --- | --- | --- |
| Story Points | 8 | Priority | High |
| Acceptance Criteria |  |  |  |
| - Aggregates game stats into season averages |  |  |  |
| - Calculates double-double and triple-double counts |  |  |  |
| - Upserts PlayerSeasonStats records |  |  |  |
| - Handles mid-season trades (player on multiple teams) |  |  |  |
| - Runs nightly or on-demand |  |  |  |
| Task | Role | Est. | Sprint |
| Create SeasonStatsAggregator class | Dev | 0.5h | In Sprint 3 |
| Implement AggregateSeasonStatsAsync method | Dev | 1h | In Sprint 3 |
| Query all PlayerGameStats for season | Dev | 0.5h | In Sprint 3 |
| Group by PlayerId, Season, TeamId | Dev | 0.5h | In Sprint 3 |
| Calculate games played and started | Dev | 0.5h | In Sprint 3 |
| Calculate average points, rebounds, assists, etc. | Dev | 1h | In Sprint 3 |
| Calculate shooting percentages | Dev | 0.5h | In Sprint 3 |
| Count double-doubles and triple-doubles | Dev | 0.5h | In Sprint 3 |
| Calculate average DraftKings fantasy score | Dev | 0.5h | In Sprint 3 |
| Upsert PlayerSeasonStats record | Dev | 1h | In Sprint 3 |
| Handle unique constraint violations | Dev | 0.5h | In Sprint 3 |
| Add logging for aggregation results | Dev | 0.5h | In Sprint 3 |
| Write unit tests for aggregation logic | Dev | 1h | In Sprint 3 |
| Create scheduled job or endpoint | Dev | 1h | In Sprint 3 |

| MBALL-314 Build Minutes Parser Utility |  |  |  |
| --- | --- | --- | --- |
| Story Points | 2 | Priority | Medium |
| Acceptance Criteria |  |  |  |
| - Parses MM:SS format correctly |  |  |  |
| - Handles edge cases: 0:30, 48:00, empty, null, invalid |  |  |  |
| - Returns (minutes, seconds) tuple |  |  |  |
| - Robust error handling |  |  |  |
| Task | Role | Est. | Sprint |
| Create MinutesParser static class | Dev | 0.5h | In Sprint 3 |
| Implement ParseMinutes method | Dev | 0.5h | In Sprint 3 |
| Split on ':' delimiter | Dev | 0.25h | In Sprint 3 |
| Parse minutes and seconds as int | Dev | 0.25h | In Sprint 3 |
| Return (0, 0) for invalid input | Dev | 0.25h | In Sprint 3 |
| Write Theory tests for all formats | Dev | 0.5h | In Sprint 3 |
| Test 32:15, 0:30, 48:00 | Dev | 0.25h | In Sprint 3 |
| Test empty string, null, invalid | Dev | 0.25h | In Sprint 3 |
| Document expected formats | Dev | 0.25h | In Sprint 3 |

| MBALL-315 Implement DNP Handling Logic |  |  |  |
| --- | --- | --- | --- |
| Story Points | 3 | Priority | Medium |
| Acceptance Criteria |  |  |  |
| - DidNotPlay flag set when player inactive |  |  |  |
| - DNPReason captured from API |  |  |  |
| - DNP games excluded from rolling averages |  |  |  |
| - DNP games excluded from season averages |  |  |  |
| - All statistics zero for DNP games |  |  |  |
| Task | Role | Est. | Sprint |
| Add DidNotPlay boolean field to entity | Dev | 0.25h | In Sprint 3 |
| Add DNPReason string field | Dev | 0.25h | In Sprint 3 |
| Parse 'Played' flag from API | Dev | 0.5h | In Sprint 3 |
| Parse 'Not_Playing_Reason' from API | Dev | 0.5h | In Sprint 3 |
| Set DidNotPlay = !dto.Played | Dev | 0.25h | In Sprint 3 |
| Set DNPReason from API field | Dev | 0.25h | In Sprint 3 |
| Set all stats to zero for DNP | Dev | 0.5h | In Sprint 3 |
| Add WHERE DidNotPlay = 0 to ML_PlayerFeatures view | Dev | 0.5h | In Sprint 3 |
| Add WHERE DidNotPlay = 0 to aggregation queries | Dev | 0.5h | In Sprint 3 |
| Test DNP handling in ingestion | Dev | 0.5h | In Sprint 3 |
| Verify DNP exclusion from features | Dev | 0.5h | In Sprint 3 |

| MBALL-320 EPIC 3: FEATURE ENGINEERING FRAMEWORK |  |  |  |  |
| --- | --- | --- | --- | --- |
| Story Points | 21 | Priority | High |  |
| Dependencies | MBALL-310 (Ingestion Pipeline) |  |  |  |

| MBALL-321 Build Rolling Average Calculator |  |  |  |
| --- | --- | --- | --- |
| Story Points | 5 | Priority | Critical |
| Acceptance Criteria |  |  |  |
| - Calculates L3, L5, L10 averages for all target stats |  |  |  |
| - Uses SQL window functions for performance |  |  |  |
| - Excludes DNP games |  |  |  |
| - Handles players with < N games gracefully |  |  |  |
| - Averages match manual calculations |  |  |  |
| Task | Role | Est. | Sprint |
| Extend ML_PlayerFeatures view | Dev | 0.5h | In Sprint 4 |
| Add Points_L3, Rebounds_L3, Assists_L3 | Dev | 1h | In Sprint 4 |
| Add ThreePointsMade_L3, Minutes_L3 | Dev | 0.5h | In Sprint 4 |
| Add L5 and L10 averages for all stats | Dev | 1h | In Sprint 4 |
| Use ROWS BETWEEN N PRECEDING AND 1 PRECEDING | Dev | 1h | In Sprint 4 |
| Partition by PlayerId, order by GameId | Dev | 0.5h | In Sprint 4 |
| Filter DidNotPlay = 0 before windowing | Dev | 0.5h | In Sprint 4 |
| Test with players having < 10 games | Dev | 0.5h | In Sprint 4 |
| Verify averages match manual calculations | Dev | 0.5h | In Sprint 4 |
| Benchmark query performance | Dev | 0.5h | In Sprint 4 |
| Add indexes if needed | Dev | 0.5h | In Sprint 4 |

| MBALL-322 Calculate Home/Away Splits |  |  |  |
| --- | --- | --- | --- |
| Story Points | 3 | Priority | High |
| Acceptance Criteria |  |  |  |
| - Points_HomeAvg calculated for all home games |  |  |  |
| - Points_AwayAvg calculated for all away games |  |  |  |
| - Splits available for all target stats |  |  |  |
| - Current game IsHomeGame flag included |  |  |  |
| Task | Role | Est. | Sprint |
| Create HomeSplits CTE in view | Dev | 0.5h | In Sprint 4 |
| Calculate AVG(Points) WHERE IsHomeGame = 1 | Dev | 0.5h | In Sprint 4 |
| Calculate AVG(Points) WHERE IsHomeGame = 0 | Dev | 0.5h | In Sprint 4 |
| Partition by PlayerId for player-specific splits | Dev | 0.5h | In Sprint 4 |
| Add splits for Rebounds, Assists, 3PM | Dev | 0.5h | In Sprint 4 |
| Join to main query | Dev | 0.25h | In Sprint 4 |
| Include IsHomeGame flag from current game | Dev | 0.25h | In Sprint 4 |
| Test splits calculation | Dev | 0.5h | In Sprint 4 |
| Verify home/away differences | Dev | 0.5h | In Sprint 4 |

| MBALL-323 Compute Rest Days and Back-to-Back |  |  |  |
| --- | --- | --- | --- |
| Story Points | 3 | Priority | Medium |
| Acceptance Criteria |  |  |  |
| - DaysSinceLastGame calculated using LAG |  |  |  |
| - IsBackToBack = 1 when days <= 1 |  |  |  |
| - Handles first game of season (NULL days) |  |  |  |
| - Feature available for all games |  |  |  |
| Task | Role | Est. | Sprint |
| Create RestDays CTE in view | Dev | 0.5h | In Sprint 4 |
| Use LAG(GameDate) OVER (PARTITION BY PlayerId ORDER BY GameId) | Dev | 0.5h | In Sprint 4 |
| Calculate DATEDIFF between current and previous game | Dev | 0.5h | In Sprint 4 |
| Set IsBackToBack = 1 when days <= 1 | Dev | 0.25h | In Sprint 4 |
| Handle NULL case (first game) | Dev | 0.25h | In Sprint 4 |
| Join to main query | Dev | 0.25h | In Sprint 4 |
| Test back-to-back detection | Dev | 0.5h | In Sprint 4 |
| Verify against actual schedules | Dev | 0.5h | In Sprint 4 |

| MBALL-324 Add Opponent Defensive Stats |  |  |  |
| --- | --- | --- | --- |
| Story Points | 5 | Priority | Medium |
| Acceptance Criteria |  |  |  |
| - OpponentTeamId identified from game context |  |  |  |
| - Join to opponent defensive averages vs position |  |  |  |
| - Defensive averages calculated per position |  |  |  |
| - Available as features for training |  |  |  |
| Task | Role | Est. | Sprint |
| Add OpponentTeamId to view (ternary based on IsHomeGame) | Dev | 0.5h | In Sprint 4 |
| Create OpponentDefense CTE | Dev | 1h | In Sprint 4 |
| Calculate opponent's average points allowed by position | Dev | 1h | In Sprint 4 |
| Group by TeamId, OpponentPosition | Dev | 0.5h | In Sprint 4 |
| Calculate avg rebounds, assists allowed | Dev | 0.5h | In Sprint 4 |
| Join to main query on OpponentTeamId and PlayerPosition | Dev | 0.5h | In Sprint 4 |
| Handle NULL position gracefully | Dev | 0.25h | In Sprint 4 |
| Test defensive stats calculation | Dev | 0.5h | In Sprint 4 |
| Verify opponent context correctness | Dev | 0.5h | In Sprint 4 |

| MBALL-325 Calculate Pace Proxy |  |  |  |
| --- | --- | --- | --- |
| Story Points | 2 | Priority | Low |
| Acceptance Criteria |  |  |  |
| - TotalScore (HomeScore + AwayScore) included |  |  |  |
| - Acts as proxy for game pace |  |  |  |
| - Available for all completed games |  |  |  |
| Task | Role | Est. | Sprint |
| Add TotalScore to GameContext CTE | Dev | 0.25h | In Sprint 4 |
| Calculate HomeScore + AwayScore | Dev | 0.25h | In Sprint 4 |
| Include in main query as OpponentPace | Dev | 0.25h | In Sprint 4 |
| Test correlation with actual pace | Dev | 0.5h | In Sprint 4 |
| Document pace proxy usage | Dev | 0.25h | In Sprint 4 |

| MBALL-326 Add Usage Proxy Placeholder |  |  |  |
| --- | --- | --- | --- |
| Story Points | 3 | Priority | Low |
| Acceptance Criteria |  |  |  |
| - UsageRate column added with placeholder calculation |  |  |  |
| - Simple approximation based on FGA + FTA |  |  |  |
| - Documentation for future enhancement |  |  |  |
| - Available as feature |  |  |  |
| Task | Role | Est. | Sprint |
| Add UsageRate calculation to view | Dev | 0.5h | In Sprint 4 |
| Approximate as (FGA + 0.44 * FTA) / MinutesPlayed | Dev | 0.5h | In Sprint 4 |
| Include in feature set | Dev | 0.25h | In Sprint 4 |
| Document as approximation | Dev | 0.25h | In Sprint 4 |
| Add TODO for true usage rate formula | Dev | 0.25h | In Sprint 4 |
| Test calculation | Dev | 0.5h | In Sprint 4 |

| MBALL-330 EPIC 4: MULTI-MODEL ML FRAMEWORK |  |  |  |  |
| --- | --- | --- | --- | --- |
| Story Points | 55 | Priority | Critical |  |
| Dependencies | MBALL-320 (Feature Engineering) |  |  |  |

| MBALL-331 Design Python ML Training Pipeline |  |  |  |
| --- | --- | --- | --- |
| Story Points | 8 | Priority | Critical |
| Acceptance Criteria |  |  |  |
| - Python environment with scikit-learn, xgboost, lightgbm |  |  |  |
| - Training script accepts stat category as parameter |  |  |  |
| - Loads features from ML_PlayerFeatures view |  |  |  |
| - Splits data into train/validation/test |  |  |  |
| - Handles missing values |  |  |  |
| - Scales features appropriately |  |  |  |
| Task | Role | Est. | Sprint |
| Create Python virtual environment | Dev | 0.5h | In Sprint 5 |
| Install scikit-learn, xgboost, lightgbm, pandas, sqlalchemy | Dev | 0.5h | In Sprint 5 |
| Create train_player_model.py script | Dev | 1h | In Sprint 5 |
| Add CLI arguments: --stat-category, --model-type | Dev | 0.5h | In Sprint 5 |
| Implement load_features_from_sql function | Dev | 1h | In Sprint 5 |
| Connect to SQL Server via sqlalchemy | Dev | 0.5h | In Sprint 5 |
| Query ML_PlayerFeatures view | Dev | 0.5h | In Sprint 5 |
| Handle NULL values (imputation or drop) | Dev | 1h | In Sprint 5 |
| Split data: 70% train, 15% validation, 15% test | Dev | 0.5h | In Sprint 5 |
| Implement StandardScaler for features | Dev | 0.5h | In Sprint 5 |
| Save scaler with model | Dev | 0.5h | In Sprint 5 |
| Add logging configuration | Dev | 0.5h | In Sprint 5 |
| Write unit tests for data loading | Dev | 1h | In Sprint 5 |

| MBALL-332 Implement Linear Regression Models |  |  |  |
| --- | --- | --- | --- |
| Story Points | 5 | Priority | High |
| Acceptance Criteria |  |  |  |
| - LinearRegression from scikit-learn |  |  |  |
| - Trained per stat category |  |  |  |
| - MAE, RMSE, R2 calculated |  |  |  |
| - Model saved as pickle file |  |  |  |
| - Baseline for comparison |  |  |  |
| Task | Role | Est. | Sprint |
| Create LinearRegressionTrainer class | Dev | 0.5h | In Sprint 5 |
| Implement train method | Dev | 0.5h | In Sprint 5 |
| Fit LinearRegression on training data | Dev | 0.5h | In Sprint 5 |
| Predict on validation set | Dev | 0.5h | In Sprint 5 |
| Calculate MAE, RMSE, R2 | Dev | 0.5h | In Sprint 5 |
| Save model to /models/Points_LinearRegression_v1.pkl | Dev | 0.5h | In Sprint 5 |
| Log metrics | Dev | 0.25h | In Sprint 5 |
| Return model metadata dictionary | Dev | 0.25h | In Sprint 5 |
| Write unit tests | Dev | 1h | In Sprint 5 |

| MBALL-333 Implement Random Forest Models |  |  |  |
| --- | --- | --- | --- |
| Story Points | 8 | Priority | High |
| Acceptance Criteria |  |  |  |
| - RandomForestRegressor from scikit-learn |  |  |  |
| - Hyperparameter tuning via GridSearchCV |  |  |  |
| - Feature importance extracted |  |  |  |
| - Cross-validation performed |  |  |  |
| - Model saved with metadata |  |  |  |
| Task | Role | Est. | Sprint |
| Create RandomForestTrainer class | Dev | 0.5h | In Sprint 5 |
| Define hyperparameter grid (n_estimators, max_depth, min_samples_split) | Dev | 0.5h | In Sprint 5 |
| Implement train method with GridSearchCV | Dev | 1h | In Sprint 5 |
| Set cv=5 for 5-fold cross-validation | Dev | 0.25h | In Sprint 5 |
| Fit on training data | Dev | 0.5h | In Sprint 5 |
| Get best_estimator_ from grid search | Dev | 0.25h | In Sprint 5 |
| Extract feature_importances_ | Dev | 0.5h | In Sprint 5 |
| Calculate validation metrics | Dev | 0.5h | In Sprint 5 |
| Calculate CV mean and std MAE | Dev | 0.5h | In Sprint 5 |
| Save best model | Dev | 0.5h | In Sprint 5 |
| Save feature importance as JSON | Dev | 0.5h | In Sprint 5 |
| Log hyperparameters and metrics | Dev | 0.25h | In Sprint 5 |
| Write unit tests | Dev | 1h | In Sprint 5 |

| MBALL-334 Implement XGBoost Models |  |  |  |
| --- | --- | --- | --- |
| Story Points | 8 | Priority | High |
| Acceptance Criteria |  |  |  |
| - XGBRegressor from xgboost |  |  |  |
| - Hyperparameter tuning |  |  |  |
| - Early stopping on validation set |  |  |  |
| - Feature importance |  |  |  |
| - Model saved |  |  |  |
| Task | Role | Est. | Sprint |
| Create XGBoostTrainer class | Dev | 0.5h | In Sprint 6 |
| Define hyperparameter grid (n_estimators, learning_rate, max_depth) | Dev | 0.5h | In Sprint 6 |
| Implement train method | Dev | 0.5h | In Sprint 6 |
| Use early_stopping_rounds=10 | Dev | 0.5h | In Sprint 6 |
| Pass validation set as eval_set | Dev | 0.25h | In Sprint 6 |
| Fit XGBRegressor | Dev | 0.5h | In Sprint 6 |
| Get best_iteration | Dev | 0.25h | In Sprint 6 |
| Extract feature_importances_ | Dev | 0.5h | In Sprint 6 |
| Calculate metrics | Dev | 0.5h | In Sprint 6 |
| Save model | Dev | 0.25h | In Sprint 6 |
| Log all hyperparameters | Dev | 0.25h | In Sprint 6 |
| Write unit tests | Dev | 1h | In Sprint 6 |

| MBALL-335 Implement LightGBM Models |  |  |  |
| --- | --- | --- | --- |
| Story Points | 8 | Priority | Medium |
| Acceptance Criteria |  |  |  |
| - LGBMRegressor from lightgbm |  |  |  |
| - Faster training than XGBoost |  |  |  |
| - Categorical feature handling |  |  |  |
| - Model saved |  |  |  |
| Task | Role | Est. | Sprint |
| Create LightGBMTrainer class | Dev | 0.5h | In Sprint 6 |
| Define hyperparameter grid | Dev | 0.5h | In Sprint 6 |
| Implement train method | Dev | 0.5h | In Sprint 6 |
| Handle categorical features (position, IsHomeGame) | Dev | 0.5h | In Sprint 6 |
| Fit LGBMRegressor | Dev | 0.5h | In Sprint 6 |
| Extract feature_importances_ | Dev | 0.5h | In Sprint 6 |
| Calculate metrics | Dev | 0.5h | In Sprint 6 |
| Save model | Dev | 0.25h | In Sprint 6 |
| Compare speed to XGBoost | Dev | 0.5h | In Sprint 6 |
| Write unit tests | Dev | 1h | In Sprint 6 |

| MBALL-336 Build Model Comparison Framework |  |  |  |
| --- | --- | --- | --- |
| Story Points | 5 | Priority | High |
| Acceptance Criteria |  |  |  |
| - Trains all models for stat category |  |  |  |
| - Compares MAE, RMSE, R2 |  |  |  |
| - Selects best model by MAE |  |  |  |
| - Logs comparison results |  |  |  |
| - Updates MLPlayerModels table |  |  |  |
| Task | Role | Est. | Sprint |
| Create ModelComparer class | Dev | 0.5h | In Sprint 6 |
| Implement compare_models_for_stat method | Dev | 0.5h | In Sprint 6 |
| Accept stat category parameter | Dev | 0.25h | In Sprint 6 |
| Train LinearRegression, RandomForest, XGBoost, LightGBM | Dev | 1h | In Sprint 6 |
| Collect metrics from each | Dev | 0.5h | In Sprint 6 |
| Sort by MAE ascending | Dev | 0.25h | In Sprint 6 |
| Select best model | Dev | 0.25h | In Sprint 6 |
| Log comparison table | Dev | 0.25h | In Sprint 6 |
| Save all models | Dev | 0.25h | In Sprint 6 |
| Mark best model in database | Dev | 0.5h | In Sprint 6 |
| Write unit tests | Dev | 1h | In Sprint 6 |

| MBALL-337 Implement Model Persistence Service |  |  |  |
| --- | --- | --- | --- |
| Story Points | 5 | Priority | High |
| Acceptance Criteria |  |  |  |
| - Saves models to /models directory |  |  |  |
| - Generates unique model names with version |  |  |  |
| - Stores metadata in MLPlayerModels table |  |  |  |
| - Loads models by ID or stat category |  |  |  |
| - Handles model versioning |  |  |  |
| Task | Role | Est. | Sprint |
| Create ModelPersistenceService class | Dev | 0.5h | In Sprint 5 |
| Implement save_model method | Dev | 0.5h | In Sprint 5 |
| Generate model filename: {Stat}_{Type}_v{Version}.pkl | Dev | 0.5h | In Sprint 5 |
| Save model file with pickle | Dev | 0.5h | In Sprint 5 |
| Insert record into MLPlayerModels table | Dev | 1h | In Sprint 5 |
| Include MAE, RMSE, R2Score, Hyperparameters, FeatureImportance | Dev | 0.5h | In Sprint 5 |
| Implement load_model method | Dev | 0.5h | In Sprint 5 |
| Load best model for stat category | Dev | 0.5h | In Sprint 5 |
| Implement set_best_model method | Dev | 0.5h | In Sprint 5 |
| Update IsBestModel flags | Dev | 0.25h | In Sprint 5 |
| Write integration tests | Dev | 1h | In Sprint 5 |

| MBALL-338 Create Cross-Validation Framework |  |  |  |
| --- | --- | --- | --- |
| Story Points | 5 | Priority | Medium |
| Acceptance Criteria |  |  |  |
| - 5-fold cross-validation |  |  |  |
| - Time-series aware split (no future data in train) |  |  |  |
| - CV metrics saved (mean, std) |  |  |  |
| - Prevents overfitting |  |  |  |
| Task | Role | Est. | Sprint |
| Implement TimeSeriesSplit from scikit-learn | Dev | 0.5h | In Sprint 6 |
| Create CrossValidator class | Dev | 0.5h | In Sprint 6 |
| Implement evaluate_with_cv method | Dev | 0.5h | In Sprint 6 |
| Perform 5-fold time-series split | Dev | 0.5h | In Sprint 6 |
| Train model on each fold | Dev | 0.5h | In Sprint 6 |
| Calculate MAE per fold | Dev | 0.5h | In Sprint 6 |
| Calculate mean and std MAE | Dev | 0.25h | In Sprint 6 |
| Log CV results | Dev | 0.25h | In Sprint 6 |
| Save CVMeanMAE and CVStdMAE to database | Dev | 0.5h | In Sprint 6 |
| Write unit tests | Dev | 1h | In Sprint 6 |

| MBALL-339 Build Hyperparameter Tuning Pipeline |  |  |  |
| --- | --- | --- | --- |
| Story Points | 8 | Priority | Medium |
| Acceptance Criteria |  |  |  |
| - GridSearchCV for exhaustive search |  |  |  |
| - RandomizedSearchCV for large spaces |  |  |  |
| - Best parameters saved with model |  |  |  |
| - Prevents overfitting |  |  |  |
| Task | Role | Est. | Sprint |
| Create HyperparameterTuner class | Dev | 0.5h | In Sprint 6 |
| Define parameter grids for each model type | Dev | 1h | In Sprint 6 |
| Implement tune_random_forest method with GridSearchCV | Dev | 1h | In Sprint 6 |
| Implement tune_xgboost method with RandomizedSearchCV | Dev | 1h | In Sprint 6 |
| Implement tune_lightgbm method | Dev | 0.5h | In Sprint 6 |
| Get best_params_ from search | Dev | 0.25h | In Sprint 6 |
| Refit on full training set | Dev | 0.5h | In Sprint 6 |
| Save hyperparameters as JSON | Dev | 0.25h | In Sprint 6 |
| Log tuning results | Dev | 0.25h | In Sprint 6 |
| Write unit tests | Dev | 1h | In Sprint 6 |

| MBALL-340 EPIC 5: PREDICTION API & INTEGRATION |  |  |  |  |
| --- | --- | --- | --- | --- |
| Story Points | 34 | Priority | High |  |
| Dependencies | MBALL-330 (ML Framework) |  |  |  |

| MBALL-341 Create Python Inference Service |  |  |  |
| --- | --- | --- | --- |
| Story Points | 8 | Priority | Critical |
| Acceptance Criteria |  |  |  |
| - predict.py script accepts player ID and game context |  |  |  |
| - Loads best model for stat category |  |  |  |
| - Generates features for upcoming game |  |  |  |
| - Returns predictions as JSON |  |  |  |
| - Handles missing models gracefully |  |  |  |
| Task | Role | Est. | Sprint |
| Create predict.py script | Dev | 0.5h | In Sprint 7 |
| Add CLI arguments: --player-id, --game-date, --opponent, --is-home | Dev | 0.5h | In Sprint 7 |
| Implement load_best_model function | Dev | 0.5h | In Sprint 7 |
| Query MLPlayerModels for IsBestModel = 1 | Dev | 0.5h | In Sprint 7 |
| Load model pickle file and scaler | Dev | 0.5h | In Sprint 7 |
| Implement generate_features_for_prediction | Dev | 1h | In Sprint 7 |
| Query player recent games and calculate rolling averages | Dev | 1h | In Sprint 7 |
| Get season averages, rest days, opponent defensive stats | Dev | 1h | In Sprint 7 |
| Scale features using saved scaler | Dev | 0.5h | In Sprint 7 |
| Predict with model and return JSON | Dev | 0.5h | In Sprint 7 |
| Handle model not found error | Dev | 0.5h | In Sprint 7 |
| Write unit tests | Dev | 1h | In Sprint 7 |

| MBALL-342 Build C# Prediction Controller |  |  |  |
| --- | --- | --- | --- |
| Story Points | 8 | Priority | Critical |
| Acceptance Criteria |  |  |  |
| - GET /api/predictions/player/{playerId} |  |  |  |
| - Query parameters: gameDate, opponentTeamId, isHome |  |  |  |
| - Calls Python script via Process |  |  |  |
| - Parses JSON response |  |  |  |
| - Returns PlayerProjectionDto |  |  |  |
| - Handles errors gracefully |  |  |  |
| Task | Role | Est. | Sprint |
| Create PredictionsController in API project | Dev | 0.5h | In Sprint 7 |
| Add GetPlayerProjection endpoint | Dev | 0.5h | In Sprint 7 |
| Accept playerId, gameDate, opponentTeamId, isHome parameters | Dev | 0.5h | In Sprint 7 |
| Validate parameters | Dev | 0.5h | In Sprint 7 |
| Create PlayerProjectionDto | Dev | 0.5h | In Sprint 7 |
| Implement PythonInferenceService | Dev | 1h | In Sprint 7 |
| Use Process.Start to call predict.py | Dev | 1h | In Sprint 7 |
| Read stdout JSON response and parse to C# object | Dev | 1h | In Sprint 7 |
| Handle stderr errors | Dev | 0.5h | In Sprint 7 |
| Return 200 OK, 404, or 500 as appropriate | Dev | 0.5h | In Sprint 7 |
| Write integration tests | Dev | 1h | In Sprint 7 |

| MBALL-343 Implement Batch Prediction Endpoint |  |  |  |
| --- | --- | --- | --- |
| Story Points | 5 | Priority | Medium |
| Acceptance Criteria |  |  |  |
| - POST /api/predictions/batch |  |  |  |
| - Accepts array of PlayerPredictionRequest |  |  |  |
| - Returns array of predictions |  |  |  |
| - Parallel processing |  |  |  |
| - Progress reporting |  |  |  |
| Task | Role | Est. | Sprint |
| Add BatchPrediction endpoint | Dev | 0.5h | In Sprint 7 |
| Accept List<PlayerPredictionRequest> in body | Dev | 0.5h | In Sprint 7 |
| Validate all requests | Dev | 0.5h | In Sprint 7 |
| Use Parallel.ForEach for concurrent predictions | Dev | 1h | In Sprint 7 |
| Collect all results | Dev | 0.5h | In Sprint 7 |
| Return List<PlayerProjectionDto> | Dev | 0.25h | In Sprint 7 |
| Add timeout per prediction | Dev | 0.5h | In Sprint 7 |
| Handle partial failures | Dev | 0.5h | In Sprint 7 |
| Log batch execution time | Dev | 0.25h | In Sprint 7 |
| Write integration tests | Dev | 1h | In Sprint 7 |

| MBALL-344 Create Prediction Caching Layer |  |  |  |
| --- | --- | --- | --- |
| Story Points | 5 | Priority | Medium |
| Acceptance Criteria |  |  |  |
| - Cache predictions for (PlayerId, GameDate, Opponent) |  |  |  |
| - TTL of 1 hour |  |  |  |
| - Redis or in-memory cache |  |  |  |
| - Cache invalidation on new data ingestion |  |  |  |
| - Reduces Python execution overhead |  |  |  |
| Task | Role | Est. | Sprint |
| Add IDistributedCache to DI | Dev | 0.25h | In Sprint 7 |
| Configure Redis or MemoryCache | Dev | 0.5h | In Sprint 7 |
| Create PredictionCacheService | Dev | 0.5h | In Sprint 7 |
| Implement GetCachedPrediction method | Dev | 0.5h | In Sprint 7 |
| Generate cache key: {playerId}_{gameDate}_{opponent} | Dev | 0.25h | In Sprint 7 |
| Check cache before Python call | Dev | 0.25h | In Sprint 7 |
| Implement SetCachedPrediction with 1 hour TTL | Dev | 0.5h | In Sprint 7 |
| Add cache hit/miss logging | Dev | 0.25h | In Sprint 7 |
| Invalidate cache on data ingestion | Dev | 0.5h | In Sprint 7 |
| Write unit tests | Dev | 1h | In Sprint 7 |

| MBALL-345 Build Prediction Confidence Scoring |  |  |  |
| --- | --- | --- | --- |
| Story Points | 5 | Priority | Low |
| Acceptance Criteria |  |  |  |
| - Confidence score (0-100) based on model metrics |  |  |  |
| - Higher confidence for lower MAE models |  |  |  |
| - Lower confidence for fewer recent games |  |  |  |
| - Included in prediction response |  |  |  |
| Task | Role | Est. | Sprint |
| Create ConfidenceCalculator class | Dev | 0.5h | In Sprint 8 |
| Implement CalculateConfidence method | Dev | 0.5h | In Sprint 8 |
| Factor in model MAE | Dev | 0.5h | In Sprint 8 |
| Factor in number of recent games available | Dev | 0.5h | In Sprint 8 |
| Factor in minutes trend | Dev | 0.5h | In Sprint 8 |
| Generate 0-100 score | Dev | 0.5h | In Sprint 8 |
| Add Confidence field to PlayerProjectionDto | Dev | 0.25h | In Sprint 8 |
| Return confidence with prediction | Dev | 0.25h | In Sprint 8 |
| Write unit tests | Dev | 1h | In Sprint 8 |

| MBALL-346 Implement Fallback Prediction Strategy |  |  |  |
| --- | --- | --- | --- |
| Story Points | 3 | Priority | Medium |
| Acceptance Criteria |  |  |  |
| - If model unavailable, use season average |  |  |  |
| - If season average unavailable, use career average |  |  |  |
| - Log fallback usage |  |  |  |
| - Return IsModelPrediction flag |  |  |  |
| Task | Role | Est. | Sprint |
| Extend PythonInferenceService | Dev | 0.25h | In Sprint 7 |
| Catch model not found exception | Dev | 0.25h | In Sprint 7 |
| Query PlayerSeasonStats for season average | Dev | 0.5h | In Sprint 7 |
| If no season stats, query all seasons for career avg | Dev | 0.5h | In Sprint 7 |
| Return fallback prediction | Dev | 0.25h | In Sprint 7 |
| Add IsModelPrediction boolean to DTO | Dev | 0.25h | In Sprint 7 |
| Log fallback reason | Dev | 0.25h | In Sprint 7 |
| Write unit tests for fallback | Dev | 0.5h | In Sprint 7 |

| MBALL-350 EPIC 6: TESTING & QUALITY ASSURANCE |  |  |  |  |
| --- | --- | --- | --- | --- |
| Story Points | 21 | Priority | High |  |
| Dependencies | All previous epics |  |  |  |

| MBALL-351 Write Unit Tests for Player Entities |  |  |  |
| --- | --- | --- | --- |
| Story Points | 5 | Priority | High |
| Acceptance Criteria |  |  |  |
| - Tests for all entity classes |  |  |  |
| - FluentAssertions throughout |  |  |  |
| - Computed column tests |  |  |  |
| - Navigation property tests |  |  |  |
| - 90%+ code coverage |  |  |  |
| Task | Role | Est. | Sprint |
| Create PlayerTests.cs | QA | 0.25h | In Sprint 8 |
| Test Player entity creation | QA | 0.5h | In Sprint 8 |
| Test FullName computed property | QA | 0.25h | In Sprint 8 |
| Create PlayerSeasonStatTests.cs | QA | 0.25h | In Sprint 8 |
| Test PointsReboundsAssists computed property | QA | 0.5h | In Sprint 8 |
| Create PlayerGameStatTests.cs | QA | 0.25h | In Sprint 8 |
| Test IsDoubleDouble, IsTripleDouble, DraftKingsFantasyScore logic | QA | 1h | In Sprint 8 |
| Use FluentAssertions Should().Be syntax | QA | 0.25h | In Sprint 8 |
| Add 'because' clauses for readability | QA | 0.25h | In Sprint 8 |
| Achieve 90%+ coverage | QA | 1h | In Sprint 8 |

| MBALL-352 Write Unit Tests for Ingestion Service |  |  |  |
| --- | --- | --- | --- |
| Story Points | 8 | Priority | High |
| Acceptance Criteria |  |  |  |
| - Tests for IngestNBAPlayersAsync |  |  |  |
| - Tests for IngestPlayerGameStatsAsync |  |  |  |
| - Idempotency tests (run twice, same result) |  |  |  |
| - DNP handling tests |  |  |  |
| - FluentAssertions throughout |  |  |  |
| Task | Role | Est. | Sprint |
| Create PlayerIngestionServiceTests.cs | QA | 0.25h | In Sprint 8 |
| Test IngestNBAPlayersAsync with mock API | QA | 1h | In Sprint 8 |
| Verify new players created | QA | 0.5h | In Sprint 8 |
| Verify existing players updated | QA | 0.5h | In Sprint 8 |
| Test idempotency (run twice, check count) | QA | 0.5h | In Sprint 8 |
| Test IngestPlayerGameStatsAsync | QA | 1h | In Sprint 8 |
| Verify stats upserted correctly | QA | 0.5h | In Sprint 8 |
| Test DNP handling (DidNotPlay = true) | QA | 0.5h | In Sprint 8 |
| Test minutes parsing | QA | 0.5h | In Sprint 8 |
| Mock repository and API service | QA | 0.5h | In Sprint 8 |
| Use FluentAssertions | QA | 0.25h | In Sprint 8 |
| Verify logging calls | QA | 0.5h | In Sprint 8 |

| MBALL-353 Write Unit Tests for Calculators |  |  |  |
| --- | --- | --- | --- |
| Story Points | 5 | Priority | High |
| Acceptance Criteria |  |  |  |
| - Tests for DerivedStatCalculator |  |  |  |
| - Tests for DraftKingsFantasyCalculator |  |  |  |
| - Theory tests for multiple scenarios |  |  |  |
| - Edge case coverage |  |  |  |
| - FluentAssertions |  |  |  |
| Task | Role | Est. | Sprint |
| Create DerivedStatCalculatorTests.cs | QA | 0.25h | In Sprint 8 |
| Test IsDoubleDouble with Theory attribute (pts+reb, pts+ast, etc.) | QA | 1h | In Sprint 8 |
| Test IsTripleDouble with Theory | QA | 0.5h | In Sprint 8 |
| Test CalculateRollingAverage with various N | QA | 0.5h | In Sprint 8 |
| Test empty games list | QA | 0.25h | In Sprint 8 |
| Create DraftKingsFantasyCalculatorTests.cs | QA | 0.25h | In Sprint 8 |
| Test basic scoring without bonuses | QA | 0.5h | In Sprint 8 |
| Test double-double bonus (+1.5) | QA | 0.25h | In Sprint 8 |
| Test triple-double bonus (+3.0, not +1.5) | QA | 0.25h | In Sprint 8 |
| Test turnover penalties | QA | 0.25h | In Sprint 8 |
| Test ProjectFantasyScore with probabilities | QA | 0.5h | In Sprint 8 |
| Use FluentAssertions with descriptive 'because' clauses | QA | 0.25h | In Sprint 8 |

| MBALL-354 Write Integration Tests for ML Pipeline |  |  |  |
| --- | --- | --- | --- |
| Story Points | 8 | Priority | Medium |
| Acceptance Criteria |  |  |  |
| - End-to-end test: train and predict |  |  |  |
| - Test on sample dataset |  |  |  |
| - Verify model persistence |  |  |  |
| - Verify predictions reasonable |  |  |  |
| - Test all model types |  |  |  |
| Task | Role | Est. | Sprint |
| Create MLPipelineIntegrationTests.py | QA | 0.5h | In Sprint 9 |
| Create sample dataset (100 games) | QA | 0.5h | In Sprint 9 |
| Test LinearRegression training and prediction | QA | 0.5h | In Sprint 9 |
| Verify model saved to file | QA | 0.25h | In Sprint 9 |
| Test RandomForest training | QA | 0.5h | In Sprint 9 |
| Test XGBoost training | QA | 0.5h | In Sprint 9 |
| Test model comparison | QA | 0.5h | In Sprint 9 |
| Verify best model selection | QA | 0.5h | In Sprint 9 |
| Test prediction with best model | QA | 0.5h | In Sprint 9 |
| Assert predictions within reasonable range | QA | 0.5h | In Sprint 9 |
| Clean up test models after | QA | 0.25h | In Sprint 9 |

| MBALL-355 Write Integration Tests for Prediction API |  |  |  |
| --- | --- | --- | --- |
| Story Points | 5 | Priority | Medium |
| Acceptance Criteria |  |  |  |
| - Test GetPlayerProjection endpoint |  |  |  |
| - Test with real player data |  |  |  |
| - Verify Python script execution |  |  |  |
| - Test error handling |  |  |  |
| - Test caching |  |  |  |
| Task | Role | Est. | Sprint |
| Create PredictionsControllerTests.cs | QA | 0.25h | In Sprint 9 |
| Setup test database with sample players | QA | 0.5h | In Sprint 9 |
| Train test model | QA | 0.5h | In Sprint 9 |
| Test GET /api/predictions/player/{id} | QA | 0.5h | In Sprint 9 |
| Verify 200 OK response with prediction values | QA | 0.5h | In Sprint 9 |
| Test with invalid player ID (404) | QA | 0.25h | In Sprint 9 |
| Test when model not found (graceful fallback) | QA | 0.25h | In Sprint 9 |
| Test caching (second call uses cache) | QA | 0.5h | In Sprint 9 |
| Test batch endpoint | QA | 0.5h | In Sprint 9 |
| Clean up test data | QA | 0.25h | In Sprint 9 |

| MBALL-360 EPIC 7: DOCUMENTATION & DEPLOYMENT |  |  |  |  |
| --- | --- | --- | --- | --- |
| Story Points | 13 | Priority | Medium |  |
| Dependencies | All previous epics |  |  |  |

| MBALL-361 Write Technical Documentation |  |  |  |
| --- | --- | --- | --- |
| Story Points | 5 | Priority | Medium |
| Acceptance Criteria |  |  |  |
| - Database schema documented |  |  |  |
| - API endpoints documented with examples |  |  |  |
| - ML pipeline documented |  |  |  |
| - Feature engineering explained |  |  |  |
| - Deployment guide |  |  |  |
| Task | Role | Est. | Sprint |
| Create README.md for player layer | Dev | 0.5h | In Sprint 9 |
| Document database tables and relationships | Dev | 1h | In Sprint 9 |
| Document API endpoints with request/response examples | Dev | 1h | In Sprint 9 |
| Document ML training process | Dev | 0.5h | In Sprint 9 |
| Explain feature engineering logic | Dev | 0.5h | In Sprint 9 |
| Document model comparison strategy | Dev | 0.5h | In Sprint 9 |
| Write deployment guide | Dev | 0.5h | In Sprint 9 |
| Add troubleshooting section | Dev | 0.5h | In Sprint 9 |
| Include performance benchmarks | Dev | 0.5h | In Sprint 9 |

| MBALL-362 Create Database Migration Scripts |  |  |  |
| --- | --- | --- | --- |
| Story Points | 3 | Priority | High |
| Acceptance Criteria |  |  |  |
| - Migration script for all tables |  |  |  |
| - Rollback script |  |  |  |
| - Seed data script for testing |  |  |  |
| - Idempotent - can run multiple times |  |  |  |
| Task | Role | Est. | Sprint |
| Create 001_CreatePlayerTables.sql | Dev | 0.5h | In Sprint 9 |
| Create Players, PlayerSeasonStats, PlayerGameStats, MLPlayerModels tables | Dev | 1h | In Sprint 9 |
| Create ML_PlayerFeatures view and all indexes | Dev | 0.5h | In Sprint 9 |
| Create 001_Rollback.sql (drop tables in reverse order) | Dev | 0.5h | In Sprint 9 |
| Create seed_test_data.sql | Dev | 0.5h | In Sprint 9 |
| Test migrations on clean database | Dev | 0.5h | In Sprint 9 |

| MBALL-363 Setup Python Environment Script |  |  |  |
| --- | --- | --- | --- |
| Story Points | 3 | Priority | Medium |
| Acceptance Criteria |  |  |  |
| - setup_ml_env.sh script |  |  |  |
| - Creates virtual environment |  |  |  |
| - Installs all dependencies |  |  |  |
| - Configures database connection |  |  |  |
| - Works on Linux and Windows |  |  |  |
| Task | Role | Est. | Sprint |
| Create setup_ml_env.sh | Dev | 0.5h | In Sprint 10 |
| Create Python virtual environment and install requirements | Dev | 0.5h | In Sprint 10 |
| Create requirements.txt with pinned versions | Dev | 0.5h | In Sprint 10 |
| Configure database connection string | Dev | 0.25h | In Sprint 10 |
| Test on Ubuntu | Dev | 0.5h | In Sprint 10 |
| Create setup_ml_env.ps1 for Windows | Dev | 0.5h | In Sprint 10 |
| Document environment setup | Dev | 0.25h | In Sprint 10 |

| MBALL-364 Create Monitoring Dashboard |  |  |  |
| --- | --- | --- | --- |
| Story Points | 5 | Priority | Low |
| Acceptance Criteria |  |  |  |
| - Dashboard shows model performance metrics |  |  |  |
| - Displays prediction accuracy over time |  |  |  |
| - Shows ingestion job status |  |  |  |
| - Alerts on errors |  |  |  |
| Task | Role | Est. | Sprint |
| Create ModelMetricsDashboard.cshtml | Dev | 0.5h | In Sprint 10 |
| Query MLPlayerModels table | Dev | 0.5h | In Sprint 10 |
| Display MAE, RMSE, R2 for each model | Dev | 0.5h | In Sprint 10 |
| Show best model per stat | Dev | 0.25h | In Sprint 10 |
| Add chart for prediction accuracy trends | Dev | 1h | In Sprint 10 |
| Show ingestion job status | Dev | 0.5h | In Sprint 10 |
| Add error alerts | Dev | 0.5h | In Sprint 10 |
| Style with Tailwind/Bootstrap | Dev | 0.5h | In Sprint 10 |

# Appendix A: Target Stat Categories

| # | Stat Category | Description |
| --- | --- | --- |
| 1 | Points | Primary scoring metric |
| 2 | Rebounds | Total rebounds (offensive + defensive) |
| 3 | Assists | Total assists |
| 4 | ThreePointsMade (3PM) | Three-pointers made |
| 5 | Steals | Total steals |
| 6 | Blocks | Total blocks |
| 7 | Turnovers | Total turnovers |
| 8 | PointsReboundsAssists (PRA) | Combined PRA stat |
| 9 | DraftKingsFantasyScore | Full DK fantasy score projection |
| 10 | DoubleDouble | Probability (0–1) |
| 11 | TripleDouble | Probability (0–1) |

# Appendix B: DraftKings Scoring Reference

| Stat | Points | Notes |
| --- | --- | --- |
| Points | 1.0 per point |  |
| 3-Pointers Made | 0.5 per 3PM |  |
| Rebounds | 1.25 per rebound |  |
| Assists | 1.5 per assist |  |
| Steals | 2.0 per steal |  |
| Blocks | 2.0 per block |  |
| Turnovers | -0.5 per turnover | Penalty |
| Double-Double Bonus | +1.5 points | When 2+ stats reach 10+ |
| Triple-Double Bonus | +3.0 points | Replaces double-double bonus; not additive |

# Appendix C: Model Types

| Model | Strengths | Use Case |
| --- | --- | --- |
| Linear Regression | Fast training, interpretable coefficients | Baseline model for comparison |
| Random Forest | Non-linear relationships, feature importance, robust to outliers | General-purpose ensemble |
| XGBoost | High performance, handles missing values, regularization | Primary competition model |
| LightGBM | Faster than XGBoost, large dataset optimization, categorical support | Speed-optimized alternative |

# Appendix D: Success Metrics

| Category | Metric | Target |
| --- | --- | --- |
| Data Quality | Complete boxscores | 100% of games |
| Data Quality | Missing player stats | < 1% |
| ML Performance | MAE – Points | < 3.0 |
| ML Performance | MAE – Rebounds | < 2.0 |
| ML Performance | MAE – Assists | < 1.5 |
| ML Performance | R2 – Best models | > 0.60 |
| System Performance | Prediction response time | < 2 seconds |
| System Performance | Ingestion throughput | < 100 games/minute |
| System Performance | API uptime | > 99% |
| Testing | Unit test coverage | > 90% |
| Testing | Integration tests | All passing |
| Testing | Critical bugs | Zero |

# Version History

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | Feb 2026 | Dev Team | Initial specification |